## Sheet1
Subcontractor ID | Start Page | End Page | G702 Page Number | Document Type | Document Category | Contractor | Mapping | Owner / COP raised to | Project | Application No. | Application Date | Period From | Period To | Contract / PO Number | Invoice Ref | Original Contract Sum | Net Change by Change Orders | Contract Sum to Date | Total Completed & Stored to Date | G702 Completed Work This Period (Gross) | G702 Total Retainage | Retainage % | Storage % | Total Earned Less Retainage | Less Previous Certificates / Payments | COP Value (Current Payment Due) | Balance to Finish | G703 Total Scheduled Value | G703 Total Work Completed Previous | G703 Total Work Completed This Period | G703 Total Materials Stored | G703 Total Completed & Stored | G703 Total Retainage | G703 Total Earned Less Retainage | G703 Balance to Finish | G702 vs G703 Check | Contractor Sign | Architect Sign | Notarized | COP Amount tying back to cost sheet | Additional Supporting Document | Vendor Name | Document Number
1 | 1 | 8 | 1 | AIA G702 | Main Document | Landmark Construction Company Inc |  | BE&K¦HITT, a joint venture | 4619-37 BSC Site Expansion PH1 | 12 | 2026-02-19 |  | 2026-02-28 |  | 89852 | 28,400,000 | 11,783,945 | 40,183,945 | 36,795,201 | 1,953,518 | 2,339,868 | 6.36 | 0 | 34,455,332 | 32,501,814 | 1,953,518 | 5,728,613 | 40,183,945 | 34,624,626 | 2,170,576 | 0 | 36,795,202 | 2,339,868 | 34,455,334 | 3,388,743 | MATCH | Yes | No | Yes | No | Transmittal | Gulf Stream Construction Company, Inc. | 14
2 | 9 | 10 | 9 | AIA G702 | Main Document | Gulf Stream Construction Co., Inc. |  | BE&K ¦ HITT, a joint venture | 251838. Boeing Pond Expansion | 6 | 2026-02-11 |  | 2026-02-28 |  | 251838.06 | 14,166,965 | 167,420 | 14,334,385 | 9,771,156 | 2,590,244 | 488,558 | 5 | 0 | 9,282,598 | 6,692,355 | 2,590,244 | 5,051,787 | 14,334,385 | 7,044,584 | 2,726,572 | 0 | 9,771,156 | 488,558 | 9,282,598 | 4,563,229 | MATCH | Yes | No | Yes | No
3 | 11 | 13 | 11 | AIA G702 | Main Document | Independence Excavating Inc |  | BEK/HITT JV | BSC Site Expansion | 5 | 2026-02-17 |  | 2026-02-28 |  |  | 15,230,000 | 20,229,975 | 35,459,975 | 5,375,288 | 2,437,788 | 268,764 | 5 |  | 5,106,523 | 2,790,625 | 2,315,898 | 30,353,452 | 35,459,975 | 2,937,500 | 2,437,788 |  | 5,375,288 | 268,764 |  | 30,084,688 | MATCH | Yes | No | Yes | No | Subcontractor Invoice | Dabico Airport Solutions, Inc. | SO64-2500800M
4 | 14 | 18 | 14 | AIA G702 | Main Document | Steelworks of the Carolinas, Inc. |  | HIIT | 25104 | 2 | 2026-02-16 |  | 2026-02-28 |  |  | 2,789,144 | 706,658 | 3,495,802 | 254,004 | 210,604 | 25,400 | 10 |  | 228,604 | 18,000 | 210,604 | 3,267,198 | 3,495,802 | 40,000 | 135,795 | 98,209 | 254,004 | 25,400 |  | 3,241,798 | MATCH | No | No | No | Yes | Bill of Sale ¦ Certificate of Liability Insurance | Steelworks of the Carolinas, Inc. ¦ Parrish & Gwinn Insurance Group LLC | NA ¦ 25-26 Inventory
5 | 19 | 21 | 19 | AIA G702 | Main Document | H&W Electrical Corp |  | BE&K ¦ HITT, a joint venture | BSC Site Expansion | 1-25122 | 02/16/2026 |  | 02/28/26 |  | 189387 | 10,731,678 | 0 | 10,731,678 | 81,500 | 81,500 | 8,150 | 10 | 10 | 73,350 | 0 | 73,350 | 10,658,328 | 10,731,678 | 81,500 | 0 | 0 | 81,500 | 8,150 | 73,350 | 10,650,178 | MATCH | Yes | No | Yes | No
6 | 22 | 23 | 22 | AIA G702 | Main Document | Landmark Construction Company Inc |  | BE&K¦HITT, a joint venture | 4631-54 Boeing PBR Roadway & Green Space | 9 | 2/13/2026 |  | 2/28/2026 |  | 89852 | 12,295,493 | 3,594,292 | 15,889,785 | 15,889,785 | 2,435,716 | 317,796 | 2 | 0 | 15,571,989 | 13,136,274 | 2,435,716 | 317,796 | 15,889,785 | 13,404,361 | 2,485,424 | 0 | 15,889,785 | 317,796 | 15,571,989 | 0 | MATCH | Yes | No | Yes | No
7 | 24 | 28 | 24 | AIA G702 | Main Document | Gulf Stream Construction Co., Inc. |  | BE&K ¦ HITT, a joint venture | 261858. Boeing South Expansion 1 & 2 | 1 | 2026-01-27 |  | 2026-01-31 |  | 261858.01 | 43,827,037 | 0 | 43,827,037 | 4,030,000 | 4,030,000 | 201,500 | 5 | 0 | 3,828,500 | 0 | 3,828,500 | 39,998,537 | 43,827,037 | 0 | 4,030,000 | 0 | 4,030,000 | 201,500 | 3,828,500 | 39,797,037 | MATCH | No | No | Yes | Yes | Partial Lien Waiver ¦ Transmittal | Gulf Stream Construction Co., Inc. ¦ Gulf Stream Construction Company, Inc. | 261858.01 ¦ 12
8 | 29 | 32 | 29 | AIA G702 | Main Document | Gulf Stream Construction Co., Inc. |  | BE&K ¦ HITT, a joint venture | 261858. Boeing South Expansion 1 & 2 | 2 | 2026-02-11 |  | 2026-02-28 |  | Invoice 261858.02 | 43,827,037 | 0 | 43,827,037 | 7,650,000 | 3,620,000 | 382,500 | 5 | 0 | 7,267,500 | 3,828,500 | 3,439,000 | 36,559,537 | 43,827,037 | 4,030,000 | 3,620,000 | 0 | 7,650,000 | 382,500 | 7,267,500 | 36,177,037 | MATCH | No | No | Yes | No | Partial Lien Waiver | Gulf Stream Construction Co., Inc. | 261858.02
9 | 33 | 35 | 33 | AIA G702 | Main Document | O.L. Thompson Construction Co., Inc |  | BE&K & HITT JV | Boeing Temp Fire Station | 6 R-1 | 2026-02-18 |  | 2026-02-28 | 196831 | PO# | 332,596 | 1,401,780 | 1,734,376 | 1,436,664 | 272,427 | 143,666 | 10 | 10 | 1,292,998 | 1,020,570 | 272,427 | 441,378 | 1,734,376 | 1,133,967 | 302,697 |  | 1,436,664 | 143,666 |  |  | MATCH | Yes | No | Yes | Yes | Change Order Summary | O.L. Thompson Construction Co., Inc | OLT-003
10 | 36 | 55 | 36 | AIA G702 | Main Document | SC Steel LLC |  | BE&K/Hitt, a joint venture | BSC Site Expansion | 9 | 2026-02-28 |  | 2026-02-28 |  | Boeing 88-48 | 102,462,000 | 23,855,152 | 126,317,152 | 54,449,497 | 4,007,640 | 5,444,950 | 10 | 10 | 49,004,547 | 44,224,261 | 4,780,286 | 77,312,605 | 126,317,152 | 49,138,069 | 4,007,640 | 1,303,789 | 54,449,497 | 5,444,950 | 49,004,547 | 71,867,655 | MATCH | Yes | No | Yes | Yes | Change Order Request Log ¦ AP Vendor Invoice Report ¦ Subcontractor Invoice ¦ Bill of Sale ¦ Certificate of Property Insurance ¦ Additional Remarks Schedule | SC Steel ¦ EVERSEIS ¦ EVER Seismic ¦ SC Steel LLC ¦ Aon Risk Services Central, Inc. ¦ Aon Risk Services Central, Inc. | NA ¦ 31-2509-7 ¦ 31-2509-7 ¦ Pay Application #9 ¦ 570117989601 ¦ 570117989601
11 | 57 | 60 | 57 | AIA G702 | Main Document | Bauer Foundations Corp |  | BE&K ¦ HITT, a joint venture | BSC Site Expansion | 6 | 15-Feb-26 |  | 28-Feb-2026 | 195411 | HITT J#: 189387 | 8,003,550 | 2,163,700 | 10,167,250 | 8,589,721 | 1,719,124 | 858,972 | 10 | 10 | 7,730,749 | 5,994,049 | 1,736,700 | 2,436,501 | 10,167,250 | 6,660,055 | 1,910,138 | 19,528 | 8,589,721 | 858,972 | 7,730,749 | 1,577,529 | MATCH | No | No | No | Yes | Affidavit of Stored Materials ¦ Bill of Sale | Bauer Foundations Corp ¦ Bauer Foundations Corp | 006 ¦ NA
12 | 61 | 68 | 61 | AIA G702 | Main Document | American Crane and Equipment Corporation |  | BE&K ¦ HITT, a joint venture | BSC Site Expansion | 22145-7 | 2026-02-16 | 2026-02-01 | 2026-02-28 | 193566 | 22145 | 73,819,000 | 533,971 | 74,352,971 | 9,909,158 | 1,113,900 | 990,916 | 10 |  | 8,918,242 | 7,915,732 | 1,002,510 | 64,443,813 | 74,352,971 | 8,795,258 | 1,113,900 | 0 | 9,909,158 | 990,916 | 8,918,242 | 64,443,813 | MATCH | Yes | No | Yes | Yes | Subcontractor Invoice ¦ Subcontractor Invoice ¦ Subcontractor Invoice ¦ Subcontractor Invoice | G.W. Becker, Inc. ¦ Concept Systems Inc ¦ Concept Systems Inc ¦ American Crane & Equipment Corp | 0086194 ¦ 25733 ¦ 25734 ¦ 22145-7
13 | 69 | 71 | 69 | AIA G702 | Main Document | Wayne Brothers Companies |  | OWNER | Boeing 88-48 Final Assembly | 7 | 2026-02-20 | 02/01/2026 | 02/28/2026 | 189387 | PO# 189387 | 41,452,021 |  | 41,452,021 | 8,083,027 | 2,905,008 | 808,303 | 10 | 10 | 7,274,725 | 4,369,716 | 2,905,008 | 34,177,296 | 41,825,388 | 4,855,240 | 3,227,787 | 0 | 8,083,027 | 808,303 | 7,274,725 | 33,742,361 | MATCH | Yes | No | Yes | Yes
14 | 72 | 117 | 72 | AIA G702 | Main Document | O.L. Thompson Construction Co., Inc |  | BE&K & HITT JV | BSC Site Expansion | 7 | 2026-02-15 |  | 2026-02-28 |  | HITT J#: 189387 | 26,636,786 | 231,739 | 26,868,525 | 15,417,757 | 3,790,746 | 1,541,776 | 10 | 10 | 13,875,982 | 10,085,235 | 3,790,746 | 12,992,543 | 26,868,525 | 11,205,817 | 4,211,940 | 0 | 15,417,757 | 1,541,776 | 13,875,982 | 11,480,828 | MATCH | Yes | No | Yes | Yes | Change Order Summary ¦ Period Total ¦ Subcontractor Invoice ¦ Email ¦ Subcontractor Invoice ¦ Subcontractor Invoice ¦ Equipment Rental Agreement ¦ Subcontractor Invoice ¦ Email ¦ Subcontractor Invoice ¦ Subcontractor Invoice ¦ Sale Agreement/Invoice | O.L. Thompson Construction Co., Inc ¦ O.L. Thompson Construction Co., Inc ¦ United Rentals ¦ Wayne Brothers ¦ Herc Rentals ¦ United Rentals ¦ Big Red Inc. ¦ Universal Sawing Group, LLC ¦ Wayne Brothers ¦ Prince's Towing, LLC ¦ Prince's Towing, LLC ¦ United Rentals | OLT-003 ¦ NA ¦ 250926451-009 ¦ NA ¦ 36102256-002 ¦ 256046367-002 ¦ NA ¦ 3635 ¦ NA ¦ 26-117511 ¦ 26-117433 ¦ 257130280-001
15 | 118 | 119 | 118 | AIA G702 | Main Document | Florence Concrete Products, Inc. |  | BE&K/HITT, A JOINT VENTURE | BSC SITE EXPANSION | 2 | 2026-02-09 |  | 2026-02-28 | JOB189387 |  | 1,750,458 | -9,575 | 1,740,883 | 548,778 | 407,751 | 54,878 | 10 | 10 | 493,900 | 126,924 | 366,976 | 1,246,983 | 1,740,883 | 141,027 | 407,751 |  | 548,778 | 54,878 | 493,900 | 1,192,105 | MATCH | Yes | No | Yes | Yes
16 | 120 | 135 | 120 | Subcontractor Requisition for Payment | Main Document | Bell Constructors, LLC |  | BE&K/Hitt a Joint Ventue | 189387 | 5 | 2026-02-15 | 2026-02-01 | 2026-02-28 | 197127 | Cost Breakdown for Billing # 5 | 95,619,000 | 4,318,468 | 99,937,468 | 4,349,998 | 286,857 | 435,000 | 10 |  | 3,914,998 | 3,656,827 |  | 96,022,470 | 99,937,468 | 4,063,142 | 286,857 | 0 | 4,349,998 | 435,000 | 3,914,998 | 95,587,470 | MATCH | Yes | No | Yes | Yes
17 | 136 | 148 | 136 | Subcontractor Requisition for Payment | Main Document | Shambaugh & Son LP |  | BE&K ¦ Hitt, a joint venture | Boeing 88-48 Assy Hangar | 4 | 2026-02-10 |  | 2026-02-28 |  | 23841504 | 14,347,770 | 113,960 | 14,461,730 | 180,000 | 45,000 | 18,000 | 10 | 10 | 162,000 | 121,500 | 40,500 | 14,299,730 | 14,461,730 | 135,000 | 45,000 | 0 | 180,000 | 18,000 |  | 14,281,730 | MATCH | Yes | No | Yes | No
18 | 149 | 152 | 149 | AIA G702 | Main Document | Eldeco, Inc |  | Agriculture Scientific, LLC | Boeing 88-48 Assembly Building | 05 | 2026-02-13 |  | 2026-02-28 | 1025115 | 2527 | 163,284,605 | 10,401,562 | 173,686,167 | 28,464,342 | 787,914 | 1,423,217 | 5 | 0 | 27,041,125 | 26,292,607 | 748,518 | 146,645,042 | 173,686,167 | 27,676,428 | 787,914 | 0 | 28,464,342 | 1,423,217 | 27,041,125 | 145,221,825 | MATCH | Yes | No | Yes | No | Subcontractor / Supplier Schedule | Eldeco, Inc | 05
19 | 153 | 155 | 153 | AIA G702 | Main Document | Glasscorp LLC |  | BE&K ¦ HITT, a joint venture | BSC Site Expansion | 3 | 02/15/26 |  | 02/28/26 | 189387 |  | 6,101,008 | 0 | 6,101,008 | 1,720,209 | 51,874 | 172,021 | 10 | 10 | 1,548,188 | 1,501,501 | 46,687 | 4,552,820 | 6,101,008 | 1,668,334 | 51,874 | 0 | 1,720,209 | 172,021 |  | 4,375,799 | MATCH | Yes | No | Yes | No | Subcontractor Invoice | GALLO MECHANICAL LLC | 6523.0226
20 | 156 | 157 | 156 | AIA G702 | Main Document | Gallo Mechanical, L.L.C. |  | BE&K ¦ HITT, a joint venture | 256523. Boeing CUP | 4 | 2026-02-12 |  | 2026-02-28 |  | Invoice #: 6523.0226 | 19,738,000 | 0 | 19,738,000 | 8,933,292 | 1,033,338 | 893,329 | 10 | 0 | 8,039,963 | 7,109,959 | 930,004 | 11,698,037 | 19,738,000 | 7,899,954 | 1,033,338 | 0 | 8,933,292 | 893,329 | 8,039,963 | 10,804,708 | MATCH | Yes | No | Yes | No
21 | 158 | 159 | 158 | AIA G702 | Main Document | STEEL CLAD |  | BE&K ¦ HITT, a joint venture | BSC Site Expansion | 1 | 2026-02-17 |  | 2026-02-28 |  | 189387 | 261,600 | 0 | 261,600 | 16,500 | 16,500 | 1,650 | 10 | 10 | 14,850 | 0 | 14,850 | 246,750 | 261,600 | 0 | 16,500 | 0 | 16,500 | 1,650 |  | 245,100 | MATCH | Yes | No | Yes | No
22 | 160 | 162 | 160 | AIA G702 | Main Document | H&W Electrical Corp |  | BE&K ¦ HITT, a joint venture | BSC Site Expansion | 4-25114 | 02/16/2026 |  | 02/28/2026 |  | 189387 | 4,691,760 | 0 | 4,691,760 | 1,236,772 | 15,000 | 123,677 | 10 | 10 | 1,113,095 | 1,099,595 | 13,500 | 3,578,665 | 4,691,760 | 1,221,772 | 15,000 | 0 | 1,236,772 | 123,677 |  | 3,454,988 | MATCH | Yes | Yes | Yes | No
23 | 163 | 164 | 163 | AIA G702 | Main Document | Shambaugh & Son, LP |  | BE&K ¦ HITT, a joint venture | BSC Site Expansion | 2 | 02/10/26 |  | 02/28/26 | 189387 |  | 321,910 | 0 | 321,910 | 17,000 | 1,000 | 1,700 | 10 | 10 | 15,300 | 14,400 | 900 | 306,610 | 321,910 | 16,000 | 1,000 | 0 | 17,000 | 1,700 |  | 304,910 | MATCH | No | No | No | No
24 | 165 | 167 | 165 | AIA G702 | Main Document | Coastal Millwork & Supply LLC |  | BE&K ¦ HITT, a joint venture | BSC Site Expansion | 1 | 2/11/26 |  | 02.28.26 |  |  | 18,455 | 0 | 18,455 | 2,620 | 2,620 | 262 | 10 | 10 | 2,358 | 0 | 2,358 | 16,097 | 18,455 | 0 | 2,620 | 0 | 2,620 | 262 |  | 15,835 | MATCH | Yes | No | Yes | No | Transmittal | Gulf Stream Construction Company, Inc. | 17
25 | 168 | 172 | 168 | AIA G702 | Main Document | Gulf Stream Construction Co., Inc. |  | BE&K ¦ HITT, a joint venture | 251829. Boeing SC Flightline T1-T4 | 7 | 2026-02-11 |  | 2026-02-28 |  | 251829.07 | 6,919,000 | 7,460,596 | 14,379,596 | 13,096,799 | 575,835 | 1,309,680 | 10 | 0 | 11,787,119 | 11,268,867 | 518,252 | 2,592,477 | 14,379,596 | 12,520,964 | 575,835 | 0 | 13,096,799 | 1,309,680 | 11,787,119 | 1,282,797 | MATCH | No | No | Yes | No | Partial Lien Waiver | Gulf Stream Construction Co., Inc. | 251829.07
26 | 173 | 174 | 173 | AIA G702 | Main Document | Independence Excavating Inc |  | BEK/HITT JV | BSC Site Expansion | 3 | 2026-02-17 |  | 2026-02-28 |  |  | 12,631,945 | 1,915,215 | 14,547,160 | 1,637,750 | 475,250 | 81,888 | 5 |  | 1,434,738 | 1,104,375 | 330,362 | 12,991,298 | 14,547,160 | 1,162,500 | 475,250 |  | 1,637,750 | 81,888 | 1,555,862 | 12,909,410 | MATCH | Yes | No | Yes | No
27 | 175 | 178 | 175 | AIA G702 | Main Document | Eldeco Inc. |  | JV of BE&K Bldg/ HITT Contracting | 3025316- BSC T1-T4 & DLO | 4 | 2/20/2026 |  | 2/28/2026 | 48855 |  | 11,642,720 | 106,226 | 11,748,946 | 5,941,860 | 2,298,468 | 297,093 | 5 | 0 | 5,644,767 | 3,346,299 | 2,298,468 | 6,104,179 | 11,748,946 | 3,522,420 | 2,419,440 |  | 5,941,860 | 297,093 | 5,807,086 |  | MATCH | Yes | No | Yes | No | Subcontractor Invoice | LITHKO CONTRACTING, LLC | 23207-006
28 | 179 | 180 | 179 | AIA G702 | Main Document | LITHKO CONTRACTING, LLC |  | BE&K/HITT Joint Venture | Boeing Temp Fire Station | 6 | 2026-02-25 |  | 2026-02-28 |  | 23207-006 | 181,820 | 948,366 | 1,130,186 | 661,661 | 133,807 | 66,166 | 10 | 0 | 595,495 | 475,069 | 120,426 | 534,691 | 1,130,186 | 527,854 | 133,807 | 0 | 661,661 | 66,166 |  | 468,525 | MATCH | Yes | No | Yes | No
29 | 181 | 184 | 181 | Subcontractor Requisition for Payment | Main Document | VSC Fire & Security, Inc. |  | HITT Contracting | Boeing Temp Fire Station | 1 | 2026-02-16 | 2026-02-01 | 2026-02-28 | PC-1050-101-00026 | 95928 | 151,127 | 0 | 151,127 | 2,110 | 2,110 | 211 | 10 |  | 1,899 | 0 | 1,899 | 149,228 | 151,127 | 0 | 2,110 | 0 | 2,110 | 211 | 1,899 | 149,017 | MATCH | Yes | No | Yes | Yes | Subcontractor Invoice ¦ Partial Lien Waiver | VSC Fire & Security, Inc. ¦ VSC Fire & Security, Inc. | INV00043874 ¦ NA
30 | 185 | 188 | 185 | AIA G702 | Main Document | Feyen Zylstra LLC |  | BE&K & HITT JV | +Boeing Temp Fire Station | 5 | 2026-02-13 |  | 2026-02-28 | Subcontract #95928 | EC25CH007 | 1,544,568 | 1,518,594 | 3,063,162 | 2,792,119 | 686,524 | 279,212 | 10 | 0 | 2,512,907 | 2,105,595 | 407,312 | 550,255 | 3,063,162 | 2,339,550 | 351,046 | 0 | 2,690,596 | 269,060 |  | 372,566 | DIFF 101,523 | Yes | No | Yes | Yes | Continuation Sheet | Feyen Zylstra LLC | 5
31 | 189 | 190 | 189 | AIA G702 | Main Document | Coastal Millwork & Supply LLC |  | BE&K ¦ HITT, a joint venture | Temporary Fire Station - IFC | 1 | 02.15.2026 |  | 02.28.2026 |  | 1 | 95,265 | 0 | 95,265 | 3,880 | 3,880 | 388 | 10 | 10 | 3,492 | 0 | 3,492 | 91,773 | 95,265 | 0 | 3,880 | 0 | 3,880 | 388 |  | 91,385 | MATCH | No | No | Yes | No
32 | 191 | 192 | 191 | AIA G702 | Main Document | DFH Commercial, Inc. |  | BE&K ¦ HITT, a joint venture | Temporary Fire Station - IFC | 2 | 2026-02-13 |  | 2026-02-28 |  |  | 97,119 | 0 | 97,119 | 38,848 | 29,136 | 3,885 | 10 |  | 34,963 | 8,741 | 26,222 | 62,156 | 97,119 | 9,712 | 29,136 | 0 | 38,848 | 3,885 | 34,963 | 58,271 | MATCH | Yes | No | Yes | No
33 | 193 | 194 | 193 | AIA G702 | Main Document | Navigator International LLC |  | BE&K / HITT | BSC Site Expansion | 26-011 APP 01Rev | 2026-02-11 |  | 2026-02-28 |  | 95928 | 624,597 |  | 624,597 | 287,143 | 287,143 | 28,714 | 10 |  | 258,429 |  | 258,429 | 366,168 | 624,597 | 0 | 287,143 | 0 | 287,143 | 28,714 |  | 337,454 | MATCH | No | No | Yes | No
34 | 195 | 196 | 195 | Subcontractor Requisition for Payment | Main Document | Jennings Air & Mechanical LLC |  | HITT CONTRACTING INC. | Boeing Temporary Fire Station | Boeing Pay App 4 | 2026-02-16 | 2026-02-01 | 2026-02-28 | 189387 | Boeing Pay App 4 | 1,805,000 | 280,000 | 2,085,000 | 568,858 | 138,658 | 56,886 | 10 |  | 511,972 | 387,180 | 124,792 | 1,167,142 | 2,085,000 | 430,200 | 138,658 |  | 568,858 | 56,886 | 511,972 | 1,167,142 | MATCH | Yes | No | Yes | No | Change Order Recap | Jennings Air & Mechanical LLC | NA
35 | 197 | 198 | 197 | AIA G702 | Main Document | Carolina Exterminating |  | BE&K ¦ HITT, a joint venture | BSC Site Expansion/TF | 1 | 02/15/26 |  | 02/28/26 |  |  | 9,125 | 0 | 9,125 | 3,125 | 3,125 | 312 | 10 | 10 | 2,812 | 0 | 2,812 | 6,312 | 9,125 | 0 | 3,125 | 0 | 3,125 | 312 | 2,813 | 0 | MATCH | Yes | No | Yes | No